## Task Table
Budget Flow — Task-Level Gantt ¦ Professional Development Plan ¦ Start: 2 June 2025
DB = Database | ENG = Engine | FE = Frontend | QA = Testing | INFRA = Setup | BE = Backend | SYNC = Sync Prep | ★ = Critical Path | MVP Phase | Premium Phase
Tasks with the same colour in 'Parallel With' column can run simultaneously. Critical path tasks (★) must complete before dependent tasks can begin.
ID | Group | Task Name | Owner | Type | Days | Start | End | Depends On | Parallel With | Priority | Risk | Critical Path | Phase / Milestone
1. Planning & Setup
T01 | 1. Planning & Setup | Project init — RN+TS, ESLint, Prettier, Jest, folder structure | Both | Infra/Setup | 3 | 2 Jun 2025 | 4 Jun 2025 | — | — | High | Low | No | MVP
↳ Establish conventions before any code is written
T02 | 1. Planning & Setup | ★ SQLite library selection + native module verification (iOS + Android) | Both | Database | 2 | 5 Jun 2025 | 6 Jun 2025 | T01 | — | Critical Path | Medium | Yes ★ | MVP
↳ op-sqlite; verify async API on both platforms before schema work
T03 | 1. Planning & Setup | CI pipeline — GitHub Actions, test runner, branch protection | Dev A | Infra/Setup | 2 | 5 Jun 2025 | 6 Jun 2025 | T01 | T02 | Medium | Low | No | MVP
↳ Run on every PR; must be green before merge
T04 | 1. Planning & Setup | Development environment docs + .env templates (dev/staging/prod) | Both | Infra/Setup | 1 | 5 Jun 2025 | 5 Jun 2025 | T01 | — | Low | Low | No | M0: Dev environment ready
↳ Appendix C of Implementation Guide
2. Database Layer
T05 | 2. Database Layer | ★ Full SQLite schema — all tables, indexes, UNIQUE constraints | Dev B | Database | 4 | 9 Jun 2025 | 12 Jun 2025 | T02 | — | Critical Path | Medium | Yes ★ | MVP
↳ Follow DB Design v2 exactly; UUID PKs, soft-delete cols, sync_status on all entities
T06 | 2. Database Layer | ★ Migration runner — versioned SQL files, schema_version table | Dev A | Database | 2 | 9 Jun 2025 | 10 Jun 2025 | T02 | T05 | Critical Path | Medium | Yes ★ | MVP
↳ PRAGMA foreign_keys=ON enforced in singleton; tested on iOS + Android
T07 | 2. Database Layer | ★ ProfileRepository — single row, essential_reserve, onboarding state | Dev A | Database | 2 | 13 Jun 2025 | 16 Jun 2025 | T05, T06 | — | Critical Path | Low | Yes ★ | MVP
↳ Establishes async Promise<T> repository pattern all others follow
T08 | 2. Database Layer | ★ PaycheckRepository — create, confirm, findCurrentCycle, softDelete | Dev A | Database | 2 | 17 Jun 2025 | 18 Jun 2025 | T07 | — | Critical Path | Low | Yes ★ | MVP
↳ Cycle anchor logic depends on this
T09 | 2. Database Layer | ★ BillRepository + BillInstanceRepository — create, update, idempotent generation | Dev A | Database | 3 | 17 Jun 2025 | 19 Jun 2025 | T07 | — | Critical Path | High Risk | Yes ★ | MVP
↳ Idempotency is the hardest part; UNIQUE(bill_id, cycle_id, due_date) enforced
T10 | 2. Database Layer | ★ PurchaseRepository — create, softDelete, findAll (deleted_at IS NULL) | Dev A | Database | 2 | 17 Jun 2025 | 18 Jun 2025 | T07 | T09 | Critical Path | Low | Yes ★ | MVP
↳ sync_queue write in same transaction as every financial write
T11 | 2. Database Layer | BalanceAdjustmentRepository + ActivityLogRepository (append-only) | Dev A | Database | 2 | 17 Jun 2025 | 18 Jun 2025 | T07 | T10 | High | Low | No | MVP
↳ No update/delete on these; sync_queue on adjustments only
T12 | 2. Database Layer | SyncQueueRepository — write path only (read path deferred to Phase 3) | Dev A | Database | 2 | 17 Jun 2025 | 18 Jun 2025 | T07 | — | High | Low | No | MVP
↳ WRITE rows from all financial repos; read engine dormant during MVP
T13 | 2. Database Layer | NotificationSettingsRepository + ImportSuggestionRepository | Dev B | Database | 2 | 17 Jun 2025 | 18 Jun 2025 | T07 | T11 | Medium | Low | No | M1: Database layer complete
↳ Single-row-per-profile pattern for notifications
3. Financial Engine
T14 | 3. Financial Engine | ★ currency.ts — integer cent arithmetic, formatCurrency(), rounding tests | Dev A | Engine | 1 | 5 Jun 2025 | 5 Jun 2025 | T01 | — | Critical Path | Low | Yes ★ | MVP
↳ Must exist before any other engine module; 100% test coverage gate
T15 | 3. Financial Engine | ★ dates.ts — ISO 8601 parsing, UTC helpers, cycle membership checks | Dev A | Engine | 1 | 5 Jun 2025 | 5 Jun 2025 | T01 | T14 | Critical Path | Low | Yes ★ | MVP
↳ Foundation for all date logic in engine
T16 | 3. Financial Engine | ★ cycleBoundaries.ts — weekly/biweekly/semimonthly/monthly, month-end edge cases | Dev A | Engine | 3 | 6 Jun 2025 | 10 Jun 2025 | T15 | — | Critical Path | High Risk | Yes ★ | MVP
↳ Semimonthly February edge cases are highest-risk date logic in project
T17 | 3. Financial Engine | ★ balance.ts — running balance from confirmed paychecks, purchases, adjustments | Dev A | Engine | 2 | 6 Jun 2025 | 9 Jun 2025 | T14 | — | Critical Path | Medium | Yes ★ | MVP
↳ Feeds directly into safe-to-spend
T18 | 3. Financial Engine | ★ safeToSpend.ts — pure function, all 6 inputs, negative result valid | Dev A | Engine | 2 | 10 Jun 2025 | 11 Jun 2025 | T17 | — | Critical Path | High Risk | Yes ★ | MVP
↳ The most important function in the codebase; result may be negative — never clamp
T19 | 3. Financial Engine | ★ billInstances.ts — fixed+variable generation, idempotency, paused exclusion | Dev B | Engine | 3 | 11 Jun 2025 | 13 Jun 2025 | T16 | — | Critical Path | High Risk | Yes ★ | MVP
↳ Duplicate prevention must be tested exhaustively
T20 | 3. Financial Engine | variableBills.ts — estimate from last confirmed, confirmation update logic | Dev B | Engine | 2 | 16 Jun 2025 | 17 Jun 2025 | T19 | — | High | Medium | No | MVP
↳ Default amount inheritance; parent bill updated on confirmation
T21 | 3. Financial Engine | projections.ts — forward cycle projections for paychecks screen | Dev B | Engine | 2 | 16 Jun 2025 | 17 Jun 2025 | T16, T19 | T20 | Medium | Medium | No | MVP
↳ Informational only; projected paychecks must NOT affect balance
T22 | 3. Financial Engine | ★ 7 acceptance test scenarios (A–G) + test contract documentation | Both | QA/Testing | 3 | 18 Jun 2025 | 20 Jun 2025 | T18, T20 | — | Critical Path | Low | Yes ★ | M2: Financial engine proven correct
↳ Gate: 100% engine coverage before any screen is built. Contracts go in /docs/calculation-contracts/
4. Services Layer
T23 | 4. Services Layer | ★ DashboardService — query repos, call engine, return DashboardState | Dev A | Engine | 2 | 19 Jun 2025 | 20 Jun 2025 | T08, T10, T18 | — | Critical Path | Low | Yes ★ | MVP
↳ First service; proves repo→engine→state chain works end to end
T24 | 4. Services Layer | ★ PurchaseService — createPurchase, deletePurchase, recalc trigger | Dev A | Engine | 2 | 23 Jun 2025 | 24 Jun 2025 | T10, T23 | — | Critical Path | Low | Yes ★ | MVP
↳ emit FINANCIAL_STATE_CHANGED after every write
T25 | 4. Services Layer | ★ PaycheckService — create, confirm, generateBillInstances on confirm | Dev A | Engine | 2 | 23 Jun 2025 | 24 Jun 2025 | T08, T09, T23 | — | Critical Path | Medium | Yes ★ | MVP
↳ Bill instance generation must be idempotent
T26 | 4. Services Layer | ★ BillService — create, update, generateInstancesForCycle, confirmVariable | Dev A | Engine | 3 | 20 Jun 2025 | 24 Jun 2025 | T09, T19, T20 | — | Critical Path | Medium | Yes ★ | MVP
↳ Most complex service; variable bill confirmation triggers recalc
T27 | 4. Services Layer | ImportService — CSV parser, field stripping, file deletion, suggestion writing | Dev A | Engine | 3 | 19 Jun 2025 | 23 Jun 2025 | T13 | — | High | High Risk | No | MVP
↳ Privacy-critical: no account numbers, raw file deleted after parse, zero network calls
T28 | 4. Services Layer | BackupService — JSON export, restore with validation + atomic transaction | Dev A | Engine | 3 | 17 Jun 2025 | 19 Jun 2025 | T07 | — | High | Medium | No | MVP
↳ Restore must be atomic; schema validation before touching any table
T29 | 4. Services Layer | ActivityLogService + NotificationService (local pending reminders) | Dev A | Engine | 2 | 17 Jun 2025 | 18 Jun 2025 | T11 | T28 | Medium | Low | No | MVP
↳ Activity log is append-only, fire-and-forget; notifications are calm/non-aggressive
5. Navigation & UI Shell
T30 | 5. Navigation & UI Shell | Bottom tab navigator + screen containers + navigation library setup | Dev B | Frontend | 2 | 6 Jun 2025 | 9 Jun 2025 | T04 | — | High | Low | No | MVP
↳ Can start parallel to schema work; empty screens only at this stage
T31 | 5. Navigation & UI Shell | ★ ProfileContext — load profile on startup, gate navigation on isLoaded | Dev B | Frontend | 1 | 17 Jun 2025 | 17 Jun 2025 | T30, T07 | — | Critical Path | Low | Yes ★ | MVP
↳ All financial screens depend on this context
T32 | 5. Navigation & UI Shell | ★ FinancialStateContext + EventBus — FINANCIAL_STATE_CHANGED propagation | Dev B | Frontend | 2 | 23 Jun 2025 | 24 Jun 2025 | T31, T23 | — | Critical Path | Medium | Yes ★ | MVP
↳ Every screen reads from this context; stale-state bugs start here
T33 | 5. Navigation & UI Shell | Shared UI components — currency display, date formatting, empty states | Dev B | Frontend | 2 | 10 Jun 2025 | 11 Jun 2025 | T30 | T31 | High | Low | No | M3: Navigation shell ready
↳ formatCurrency() from engine is the only place division-by-100 happens
6. Dashboard
T34 | 6. Dashboard | ★ DashboardScreen — safe-to-spend hero, upcoming bills, next paycheck | Dev B | Frontend | 3 | 25 Jun 2025 | 27 Jun 2025 | T32, T23, T33 | — | Critical Path | Medium | Yes ★ | MVP
↳ Most important screen; safe-to-spend must recalc < 50ms on mid-range device
T35 | 6. Dashboard | Safe-to-spend negative state display — red styling, no clamping to zero | Dev B | Frontend | 1 | 30 Jun 2025 | 30 Jun 2025 | T34 | — | High | Low | No | M4: Dashboard working end-to-end
↳ A negative STS is valid and meaningful; never display 0 when actual is negative
7. Purchases
T36 | 7. Purchases | ★ PurchasesScreen — transaction list, cycle grouping, pending badges | Dev B | Frontend | 2 | 25 Jun 2025 | 26 Jun 2025 | T32, T33, T24 | — | Critical Path | Low | Yes ★ | MVP
T37 | 7. Purchases | ★ PurchaseEntrySheet — amount input, charged/pending toggle, instant STS update | Dev B | Frontend | 2 | 27 Jun 2025 | 30 Jun 2025 | T36 | — | Critical Path | Medium | Yes ★ | MVP
↳ Pending purchase must reduce STS immediately on entry, same as charged
8. Bills
T38 | 8. Bills | ★ BillsScreen — cycle grouping, due-date sort, fixed vs variable indicators | Dev B | Frontend | 2 | 25 Jun 2025 | 26 Jun 2025 | T32, T33, T26 | — | Critical Path | Medium | Yes ★ | MVP
↳ Estimated variable bills must be clearly labelled
T39 | 8. Bills | VariableBillConfirmSheet — enter actual amount, trigger recalc | Dev B | Frontend | 2 | 27 Jun 2025 | 30 Jun 2025 | T38, T26 | — | High | Medium | No | MVP
↳ Confirmation updates parent bill.default_amount_cents for future cycles
T40 | 8. Bills | Bill add/edit form — recurrence interval, end date, pause toggle | Dev B | Frontend | 2 | 27 Jun 2025 | 30 Jun 2025 | T38 | — | High | Low | No | MVP
↳ Pause does not delete; is_paused=1 excludes from STS deductions
9. Paychecks
T41 | 9. Paychecks | PaychecksScreen — cycle cards, projected vs confirmed state, swipe nav | Dev B | Frontend | 3 | 25 Jun 2025 | 27 Jun 2025 | T32, T33, T25, T21 | — | High | Medium | No | MVP
↳ Projected paychecks shown but must NOT affect balance until confirmed
T42 | 9. Paychecks | ★ Paycheck confirm flow — mark received, trigger bill instance generation | Dev B | Frontend | 1 | 30 Jun 2025 | 30 Jun 2025 | T41, T25 | — | Critical Path | Low | Yes ★ | MVP
↳ Confirming paycheck is the single most impactful user action
10. Import
T43 | 10. Import | ImportScreen — file picker, processing state, privacy confirmation | Dev B | Frontend | 2 | 24 Jun 2025 | 25 Jun 2025 | T30, T27 | — | High | Medium | No | MVP
↳ No upload progress spinner should suggest file left device
T44 | 10. Import | SuggestionReviewScreen — confirm/reject each detected recurring expense | Dev B | Frontend | 2 | 26 Jun 2025 | 27 Jun 2025 | T43 | — | High | Medium | No | MVP
↳ Rejection must produce zero writes to bills table
11. Settings & Backup
T45 | 11. Settings & Backup | SettingsScreen — reserve config, notification prefs, backup/restore | Dev B | Frontend | 2 | 25 Jun 2025 | 26 Jun 2025 | T32, T28, T29 | — | High | Low | No | MVP
T46 | 11. Settings & Backup | BackupRestoreScreen — export, import, file validation feedback | Dev B | Frontend | 2 | 27 Jun 2025 | 30 Jun 2025 | T45, T28 | — | High | Medium | No | MVP
↳ Validate JSON schema before starting restore transaction
T47 | 11. Settings & Backup | Onboarding flow — skippable steps, partial dashboard still functional | Dev B | Frontend | 3 | 30 Jun 2025 | 2 Jul 2025 | T34, T36, T38, T41 | — | Medium | Low | No | M5: MVP feature complete
↳ Build last; onboarding wraps existing features — if features have bugs, onboarding surfaces them
12. QA & Polish
T48 | 12. QA & Polish | ★ Integration test suite — sync_queue writes, soft deletes, FK enforcement | Both | QA/Testing | 3 | 3 Jul 2025 | 7 Jul 2025 | T22, T47 | — | Critical Path | Medium | Yes ★ | MVP
↳ Real SQLite in-memory DB; seed known state, assert correct STS
T49 | 12. QA & Polish | ★ Physical device QA — 7 acceptance scenarios on iOS + Android | Both | QA/Testing | 3 | 8 Jul 2025 | 10 Jul 2025 | T48 | — | Critical Path | High Risk | Yes ★ | MVP
↳ Airplane mode verification; no network calls in any MVP operation path
T50 | 12. QA & Polish | Performance audit — STS recalc < 50ms, SQLite EXPLAIN QUERY PLAN | Dev A | QA/Testing | 2 | 11 Jul 2025 | 14 Jul 2025 | T49 | — | High | Medium | No | MVP
↳ If slow, add indexes; never mask with loading spinner
T51 | 12. QA & Polish | Accessibility pass — VoiceOver (iOS) + TalkBack (Android), font scaling | Dev B | QA/Testing | 2 | 11 Jul 2025 | 14 Jul 2025 | T49 | T50 | High | Low | No | MVP
↳ 200% font scaling must not overflow
T52 | 12. QA & Polish | ★ Import privacy verification — no sensitive fields, file deletion confirmed | Both | QA/Testing | 1 | 11 Jul 2025 | 11 Jul 2025 | T49 | — | Critical Path | High Risk | Yes ★ | MVP
↳ Assert: no account numbers in import_suggestions; file path inaccessible after parse
13. Beta & Launch
T53 | 13. Beta & Launch | Crash reporting setup — Sentry, beforeSend strips all financial data | Dev A | Infra/Setup | 2 | 11 Jul 2025 | 14 Jul 2025 | T49 | — | High | Medium | No | MVP
↳ Never transmit financial data in crash reports
T54 | 13. Beta & Launch | App Store + Play Store assets — screenshots, descriptions, privacy labels | Dev B | Frontend | 3 | 11 Jul 2025 | 15 Jul 2025 | T51 | T53 | High | Low | No | MVP
↳ Privacy label: data not collected, not linked to identity
T55 | 13. Beta & Launch | TestFlight (iOS) + Internal Testing (Android) beta distribution | Both | Infra/Setup | 2 | 16 Jul 2025 | 17 Jul 2025 | T53, T54 | — | High | Medium | No | MVP
T56 | 13. Beta & Launch | Beta feedback triage + critical fixes + final store submission | Both | QA/Testing | 3 | 18 Jul 2025 | 22 Jul 2025 | T55 | — | High | High Risk | No | M6: App Store submitted — MVP shipped
14. Sync Prep
T57 | 14. Sync Prep | sync_queue audit — verify all repos write rows on create/update/delete | Dev A | Sync | 2 | 8 Jul 2025 | 9 Jul 2025 | T48 | — | High | Medium | No | MVP
↳ Write a test that asserts sync_queue written for every sync-eligible entity
T58 | 14. Sync Prep | Calculation contracts documentation — /docs/calculation-contracts/ | Both | Sync | 2 | 23 Jun 2025 | 24 Jun 2025 | T22 | T57 | High | Low | No | MVP
↳ Named input/output contracts; reused as Phase 3 parity test inputs
T59 | 14. Sync Prep | SyncEngine stub — feature-flagged no-op, FEATURE_PREMIUM_SYNC=false | Dev A | Sync | 1 | 10 Jul 2025 | 10 Jul 2025 | T57 | — | Medium | Low | No | M7: MVP sync scaffolding verified
↳ start() returns immediately in MVP; Phase 3 activates real logic
15. Backend Setup
T60 | 15. Backend Setup | Spring Boot project init — modules, PostgreSQL schema (+device_id, cloud_id cols) | Dev A | Backend | 4 | 23 Jul 2025 | 28 Jul 2025 | T56 | — | High | Medium | No | Premium
↳ Schema mirrors SQLite for sync-eligible entities
T61 | 15. Backend Setup | ★ Auth module — register, bcrypt, login, JWT RS256 sign/verify | Dev A | Backend | 4 | 29 Jul 2025 | 1 Aug 2025 | T60 | — | Critical Path | Medium | Yes ★ | Premium
↳ RS256 asymmetric; private key env var only, never in code
T62 | 15. Backend Setup | ★ Accounts module — profile_id ↔ user_id linkage, first-sync registration | Dev A | Backend | 2 | 4 Aug 2025 | 5 Aug 2025 | T61 | — | Critical Path | Medium | Yes ★ | Premium
↳ profile_id never changes; user_id is cloud auth layer only
T63 | 15. Backend Setup | Mobile auth UI — registration/login screens, Keychain/Keystore token storage | Dev B | Frontend | 3 | 29 Jul 2025 | 31 Jul 2025 | T60 | — | High | Medium | No | Premium
↳ Never AsyncStorage for tokens
T64 | 15. Backend Setup | 401 interceptor + token refresh logic in API client | Dev B | Frontend | 2 | 4 Aug 2025 | 5 Aug 2025 | T63, T61 | — | High | Medium | No | M8: Auth working
↳ Access token 60min; refresh token 30d
16. Sync Engine
T65 | 16. Sync Engine | ★ POST /v1/sync/push — receive records, LWW upsert, return queue_entry_id results | Dev A | Backend | 4 | 6 Aug 2025 | 11 Aug 2025 | T62 | — | Critical Path | High Risk | Yes ★ | Premium
↳ last-write-wins on client_updated_at; conflict detail returned on loss
T66 | 16. Sync Engine | ★ SyncEngine.ts activation — read sync_queue, batch push, exponential backoff | Dev B | Sync | 4 | 6 Aug 2025 | 11 Aug 2025 | T59, T64 | — | Critical Path | High Risk | Yes ★ | Premium
↳ Process ORDER BY created_at ASC; reset 'syncing' to 'pending' on startup
T67 | 16. Sync Engine | ★ GET /v1/sync/pull — records since cursor, server_updated_at in response | Dev A | Backend | 3 | 12 Aug 2025 | 14 Aug 2025 | T65 | — | Critical Path | High Risk | Yes ★ | Premium
↳ Cursor saved atomically with pull results in same transaction
T68 | 16. Sync Engine | ★ Pull apply — LWW, local-pending-beats-pull rule, cursor persistence | Dev B | Sync | 3 | 15 Aug 2025 | 19 Aug 2025 | T66, T67 | — | Critical Path | High Risk | Yes ★ | Premium
↳ Skip pull update if pending sync_queue entry exists for that entity_id
17. Shared Business Rules
T69 | 17. Shared Business Rules | Backend financial engine — mirror safeToSpend rules in Spring Boot | Dev A | Backend | 4 | 12 Aug 2025 | 15 Aug 2025 | T65 | — | High | High Risk | No | Premium
↳ Use /docs/calculation-contracts/ as acceptance criteria; parity to the cent
T70 | 17. Shared Business Rules | ★ Parity tests — seed identical state in SQLite + PostgreSQL, assert equal STS | Both | QA/Testing | 3 | 20 Aug 2025 | 22 Aug 2025 | T69, T68 | — | Critical Path | High Risk | Yes ★ | M9: Sync + parity proven
↳ Any divergence is a blocking defect — not a tolerance issue
18. Cloud & Notifications
T71 | 18. Cloud & Notifications | Cloud backup endpoints — POST/GET /v1/backup | Dev A | Backend | 2 | 6 Aug 2025 | 7 Aug 2025 | T62 | — | Medium | Low | No | Premium
T72 | 18. Cloud & Notifications | Cloud backup UI — enable toggle, restore from cloud in Settings | Dev B | Frontend | 2 | 8 Aug 2025 | 11 Aug 2025 | T71, T45 | — | Medium | Low | No | Premium
T73 | 18. Cloud & Notifications | Server-side notifications — APNs + FCM, calm tone, bill reminders | Dev A | Backend | 3 | 12 Aug 2025 | 14 Aug 2025 | T65 | — | Medium | Medium | No | Premium
↳ Tone rules from FRS must be enforced at backend level too
T74 | 18. Cloud & Notifications | Premium UX — sync status, premium onboarding, notification prefs | Dev B | Frontend | 3 | 15 Aug 2025 | 19 Aug 2025 | T72, T73, T66 | — | Medium | Medium | No | Premium
19. Premium QA
T75 | 19. Premium QA | ★ Full regression suite — all MVP tests still green post-Phase 3 | Both | QA/Testing | 2 | 25 Aug 2025 | 26 Aug 2025 | T70, T74 | — | Critical Path | Medium | Yes ★ | Premium
↳ Zero regressions allowed
T76 | 19. Premium QA | Multi-device conflict test — two devices edit same record, newer wins | Both | QA/Testing | 2 | 25 Aug 2025 | 26 Aug 2025 | T70 | — | High | High Risk | No | Premium
T77 | 19. Premium QA | Backend deploy — PostgreSQL, Spring Boot, health checks, monitoring | Dev A | Infra/Setup | 2 | 27 Aug 2025 | 28 Aug 2025 | T75, T76 | — | High | Medium | No | Premium
T78 | 19. Premium QA | Premium store update + feature flag flip + launch | Both | Infra/Setup | 2 | 29 Aug 2025 | 1 Sep 2025 | T77 | — | High | Low | No | M10: Premium launch
20. Web Prep (Future)
T79 | 20. Web Prep (Future) | Backend engine web API endpoints — serve STS for web clients | Dev A | Backend | 3 | 18 Aug 2025 | 20 Aug 2025 | T69 | — | Low | Medium | No | Future
↳ Parallel implementation; mobile authority unchanged
T80 | 20. Web Prep (Future) | Web client scaffolding — React web app, consume backend engine API | Dev B | Frontend | 5 | 21 Aug 2025 | 27 Aug 2025 | T79 | — | Low | High Risk | No | M11: Web client foundation
↳ Out of scope until premium sync is stable

## Visual Gantt
Budget Flow — Visual Gantt Chart ¦ 80 tasks · 3 phases · Start 2 June 2025
|  |  | Phase 1 & 2 — MVP + Polish | [6 empty] | Phase 3 — Premium Sync
|  |  | Jun 2025 |  |  |  | Jul 2025 |  |  |  | Aug 2025 |  |  |  | Sep 2025
ID | Task Name | Owner | W1 |  | W3 | W5 |  | W7 |  | W9 |  | W11 |  | W13
1. Planning & Setup
T01 | Project init — RN+TS, ESLint, Prettier, Jest, folder structure | Both
T02 | ★ SQLite library selection + native module verification (iOS + Android) | Both
T03 | CI pipeline — GitHub Actions, test runner, branch protection | Dev A
T04 | Development environment docs + .env templates (dev/staging/prod) | Both | ◆
◆ M0: Dev environment ready
2. Database Layer
T05 | ★ Full SQLite schema — all tables, indexes, UNIQUE constraints | Dev B
T06 | ★ Migration runner — versioned SQL files, schema_version table | Dev A
T07 | ★ ProfileRepository — single row, essential_reserve, onboarding state | Dev A
T08 | ★ PaycheckRepository — create, confirm, findCurrentCycle, softDelete | Dev A
T09 | ★ BillRepository + BillInstanceRepository — create, update, idempotent generation | Dev A
T10 | ★ PurchaseRepository — create, softDelete, findAll (deleted_at IS NULL) | Dev A
T11 | BalanceAdjustmentRepository + ActivityLogRepository (append-only) | Dev A
T12 | SyncQueueRepository — write path only (read path deferred to Phase 3) | Dev A
T13 | NotificationSettingsRepository + ImportSuggestionRepository | Dev B |  |  | ◆
◆ M1: Database layer complete
3. Financial Engine
T14 | ★ currency.ts — integer cent arithmetic, formatCurrency(), rounding tests | Dev A
T15 | ★ dates.ts — ISO 8601 parsing, UTC helpers, cycle membership checks | Dev A
T16 | ★ cycleBoundaries.ts — weekly/biweekly/semimonthly/monthly, month-end edge cases | Dev A
T17 | ★ balance.ts — running balance from confirmed paychecks, purchases, adjustments | Dev A
T18 | ★ safeToSpend.ts — pure function, all 6 inputs, negative result valid | Dev A
T19 | ★ billInstances.ts — fixed+variable generation, idempotency, paused exclusion | Dev B
T20 | variableBills.ts — estimate from last confirmed, confirmation update logic | Dev B
T21 | projections.ts — forward cycle projections for paychecks screen | Dev B
T22 | ★ 7 acceptance test scenarios (A–G) + test contract documentation | Both |  |  | ◆
◆ M2: Financial engine proven correct
4. Services Layer
T23 | ★ DashboardService — query repos, call engine, return DashboardState | Dev A
T24 | ★ PurchaseService — createPurchase, deletePurchase, recalc trigger | Dev A
T25 | ★ PaycheckService — create, confirm, generateBillInstances on confirm | Dev A
T26 | ★ BillService — create, update, generateInstancesForCycle, confirmVariable | Dev A
T27 | ImportService — CSV parser, field stripping, file deletion, suggestion writing | Dev A
T28 | BackupService — JSON export, restore with validation + atomic transaction | Dev A
T29 | ActivityLogService + NotificationService (local pending reminders) | Dev A
5. Navigation & UI Shell
T30 | Bottom tab navigator + screen containers + navigation library setup | Dev B
T31 | ★ ProfileContext — load profile on startup, gate navigation on isLoaded | Dev B
T32 | ★ FinancialStateContext + EventBus — FINANCIAL_STATE_CHANGED propagation | Dev B
T33 | Shared UI components — currency display, date formatting, empty states | Dev B |  | ◆
◆ M3: Navigation shell ready
6. Dashboard
T34 | ★ DashboardScreen — safe-to-spend hero, upcoming bills, next paycheck | Dev B
T35 | Safe-to-spend negative state display — red styling, no clamping to zero | Dev B |  |  |  | ◆
◆ M4: Dashboard working end-to-end
7. Purchases
T36 | ★ PurchasesScreen — transaction list, cycle grouping, pending badges | Dev B
T37 | ★ PurchaseEntrySheet — amount input, charged/pending toggle, instant STS update | Dev B
8. Bills
T38 | ★ BillsScreen — cycle grouping, due-date sort, fixed vs variable indicators | Dev B
T39 | VariableBillConfirmSheet — enter actual amount, trigger recalc | Dev B
T40 | Bill add/edit form — recurrence interval, end date, pause toggle | Dev B
9. Paychecks
T41 | PaychecksScreen — cycle cards, projected vs confirmed state, swipe nav | Dev B
T42 | ★ Paycheck confirm flow — mark received, trigger bill instance generation | Dev B
10. Import
T43 | ImportScreen — file picker, processing state, privacy confirmation | Dev B
T44 | SuggestionReviewScreen — confirm/reject each detected recurring expense | Dev B
11. Settings & Backup
T45 | SettingsScreen — reserve config, notification prefs, backup/restore | Dev B
T46 | BackupRestoreScreen — export, import, file validation feedback | Dev B
T47 | Onboarding flow — skippable steps, partial dashboard still functional | Dev B |  |  |  | ◆
◆ M5: MVP feature complete
12. QA & Polish
T48 | ★ Integration test suite — sync_queue writes, soft deletes, FK enforcement | Both
T49 | ★ Physical device QA — 7 acceptance scenarios on iOS + Android | Both
T50 | Performance audit — STS recalc < 50ms, SQLite EXPLAIN QUERY PLAN | Dev A
T51 | Accessibility pass — VoiceOver (iOS) + TalkBack (Android), font scaling | Dev B
T52 | ★ Import privacy verification — no sensitive fields, file deletion confirmed | Both
13. Beta & Launch
T53 | Crash reporting setup — Sentry, beforeSend strips all financial data | Dev A
T54 | App Store + Play Store assets — screenshots, descriptions, privacy labels | Dev B
T55 | TestFlight (iOS) + Internal Testing (Android) beta distribution | Both
T56 | Beta feedback triage + critical fixes + final store submission | Both | [6 empty] | ◆
◆ M6: App Store submitted — MVP shipped
14. Sync Prep
T57 | sync_queue audit — verify all repos write rows on create/update/delete | Dev A
T58 | Calculation contracts documentation — /docs/calculation-contracts/ | Both
T59 | SyncEngine stub — feature-flagged no-op, FEATURE_PREMIUM_SYNC=false | Dev A |  |  |  |  | ◆
◆ M7: MVP sync scaffolding verified
15. Backend Setup
T60 | Spring Boot project init — modules, PostgreSQL schema (+device_id, cloud_id cols) | Dev A
T61 | ★ Auth module — register, bcrypt, login, JWT RS256 sign/verify | Dev A
T62 | ★ Accounts module — profile_id ↔ user_id linkage, first-sync registration | Dev A
T63 | Mobile auth UI — registration/login screens, Keychain/Keystore token storage | Dev B
T64 | 401 interceptor + token refresh logic in API client | Dev B | [8 empty] | ◆
◆ M8: Auth working
16. Sync Engine
T65 | ★ POST /v1/sync/push — receive records, LWW upsert, return queue_entry_id results | Dev A
T66 | ★ SyncEngine.ts activation — read sync_queue, batch push, exponential backoff | Dev B
T67 | ★ GET /v1/sync/pull — records since cursor, server_updated_at in response | Dev A
T68 | ★ Pull apply — LWW, local-pending-beats-pull rule, cursor persistence | Dev B
17. Shared Business Rules
T69 | Backend financial engine — mirror safeToSpend rules in Spring Boot | Dev A
T70 | ★ Parity tests — seed identical state in SQLite + PostgreSQL, assert equal STS | Both | [10 empty] | ◆
◆ M9: Sync + parity proven
18. Cloud & Notifications
T71 | Cloud backup endpoints — POST/GET /v1/backup | Dev A
T72 | Cloud backup UI — enable toggle, restore from cloud in Settings | Dev B
T73 | Server-side notifications — APNs + FCM, calm tone, bill reminders | Dev A
T74 | Premium UX — sync status, premium onboarding, notification prefs | Dev B
19. Premium QA
T75 | ★ Full regression suite — all MVP tests still green post-Phase 3 | Both
T76 | Multi-device conflict test — two devices edit same record, newer wins | Both
T77 | Backend deploy — PostgreSQL, Spring Boot, health checks, monitoring | Dev A
T78 | Premium store update + feature flag flip + launch | Both | [12 empty] | ◆
◆ M10: Premium launch
20. Web Prep (Future)
T79 | Backend engine web API endpoints — serve STS for web clients | Dev A
T80 | Web client scaffolding — React web app, consume backend engine API | Dev B | [11 empty] | ◆
◆ M11: Web client foundation

## Critical Path & Risk
Budget Flow — Critical Path & Risk Analysis
ID | Group | Task | Days | Start | End | Why Critical
CRITICAL PATH — 36 tasks ¦ These must complete on time. Delays here delay the entire project.
T02 | 1. Planning & Setup | SQLite library selection + native module verification (iOS + Android) | 2 | 5 Jun | 6 Jun | SQLite library choice gates all DB work; switching mid-project rewrites every repo
T05 | 2. Database Layer | Full SQLite schema — all tables, indexes, UNIQUE constraints | 4 | 9 Jun | 12 Jun | Schema is the foundation; every layer above depends on field names and types
T06 | 2. Database Layer | Migration runner — versioned SQL files, schema_version table | 2 | 9 Jun | 10 Jun | Migration runner must work on both platforms before any feature code is written
T07 | 2. Database Layer | ProfileRepository — single row, essential_reserve, onboarding state | 2 | 13 Jun | 16 Jun | Async Promise<T> pattern set here is inherited by all 8 other repositories
T08 | 2. Database Layer | PaycheckRepository — create, confirm, findCurrentCycle, softDelete | 2 | 17 Jun | 18 Jun | Cycle anchor logic — paychecks define the time windows bills/purchases group into
T09 | 2. Database Layer | BillRepository + BillInstanceRepository — create, update, idempotent generation | 3 | 17 Jun | 19 Jun | Bill instance idempotency is the hardest data correctness problem in the schema
T10 | 2. Database Layer | PurchaseRepository — create, softDelete, findAll (deleted_at IS NULL) | 2 | 17 Jun | 18 Jun | Every financial action writes a purchase; sync_queue write must be in same transaction
T14 | 3. Financial Engine | currency.ts — integer cent arithmetic, formatCurrency(), rounding tests | 1 | 5 Jun | 5 Jun | Integer-cent arithmetic must exist before any monetary calculation is written
T15 | 3. Financial Engine | dates.ts — ISO 8601 parsing, UTC helpers, cycle membership checks | 1 | 5 Jun | 5 Jun | Date utilities underpin cycle boundaries, due dates, and ISO 8601 timestamp handling
T16 | 3. Financial Engine | cycleBoundaries.ts — weekly/biweekly/semimonthly/monthly, month-end edge cases | 3 | 6 Jun | 10 Jun | Cycle boundaries are the most error-prone engine logic; semimonthly Feb edge cases
T17 | 3. Financial Engine | balance.ts — running balance from confirmed paychecks, purchases, adjustments | 2 | 6 Jun | 9 Jun | Running balance feeds directly into safe-to-spend; errors here corrupt the primary number
T18 | 3. Financial Engine | safeToSpend.ts — pure function, all 6 inputs, negative result valid | 2 | 10 Jun | 11 Jun | safe-to-spend IS the app; 100% test coverage is a hard gate before any screen is built
T19 | 3. Financial Engine | billInstances.ts — fixed+variable generation, idempotency, paused exclusion | 3 | 11 Jun | 13 Jun | Bill instance generation must be idempotent; duplicate instances double-deduct safe-to-spend
T22 | 3. Financial Engine | 7 acceptance test scenarios (A–G) + test contract documentation | 3 | 18 Jun | 20 Jun | All 7 acceptance scenarios must pass before Sprint 3; test contracts reused in Phase 3
T23 | 4. Services Layer | DashboardService — query repos, call engine, return DashboardState | 2 | 19 Jun | 20 Jun | First service; proves the repo → engine → state chain works end-to-end
T24 | 4. Services Layer | PurchaseService — createPurchase, deletePurchase, recalc trigger | 2 | 23 Jun | 24 Jun | Purchase creation is the most frequent user action; any bug here is immediately visible
T25 | 4. Services Layer | PaycheckService — create, confirm, generateBillInstances on confirm | 2 | 23 Jun | 24 Jun | Paycheck confirmation triggers bill generation; this is the highest-impact single action
T26 | 4. Services Layer | BillService — create, update, generateInstancesForCycle, confirmVariable | 3 | 20 Jun | 24 Jun | Most complex service; variable bill confirmation is a multi-step recalculation chain
T31 | 5. Navigation & UI Shell | ProfileContext — load profile on startup, gate navigation on isLoaded | 1 | 17 Jun | 17 Jun | All financial screens are gated on this context; wrong profile = wrong data everywhere
T32 | 5. Navigation & UI Shell | FinancialStateContext + EventBus — FINANCIAL_STATE_CHANGED propagation | 2 | 23 Jun | 24 Jun | EventBus wiring is the recalculation backbone; missed events = stale safe-to-spend
T34 | 6. Dashboard | DashboardScreen — safe-to-spend hero, upcoming bills, next paycheck | 3 | 25 Jun | 27 Jun | Dashboard is the first thing users see; correctness here proves the entire stack works
T36 | 7. Purchases | PurchasesScreen — transaction list, cycle grouping, pending badges | 2 | 25 Jun | 26 Jun | Purchase entry is the most frequent daily action
T37 | 7. Purchases | PurchaseEntrySheet — amount input, charged/pending toggle, instant STS update | 2 | 27 Jun | 30 Jun | Pending purchases must reduce STS immediately — this is an FRS hard requirement
T38 | 8. Bills | BillsScreen — cycle grouping, due-date sort, fixed vs variable indicators | 2 | 25 Jun | 26 Jun | Bills screen displays variable bill estimates; incorrect labels destroy user trust
T42 | 9. Paychecks | Paycheck confirm flow — mark received, trigger bill instance generation | 1 | 30 Jun | 30 Jun | Confirming a paycheck is the single most impactful user action in the app
T48 | 12. QA & Polish | Integration test suite — sync_queue writes, soft deletes, FK enforcement | 3 | 3 Jul | 7 Jul | Integration tests with real SQLite prove sync_queue + soft deletes work together
T49 | 12. QA & Polish | Physical device QA — 7 acceptance scenarios on iOS + Android | 3 | 8 Jul | 10 Jul | Physical device QA in airplane mode is the MVP release gate
T52 | 12. QA & Polish | Import privacy verification — no sensitive fields, file deletion confirmed | 1 | 11 Jul | 11 Jul | Import privacy is a legal and trust requirement; failure here is a critical bug
T61 | 15. Backend Setup | Auth module — register, bcrypt, login, JWT RS256 sign/verify | 4 | 29 Jul | 1 Aug | JWT RS256 auth is the security foundation for all Phase 3 endpoints
T62 | 15. Backend Setup | Accounts module — profile_id ↔ user_id linkage, first-sync registration | 2 | 4 Aug | 5 Aug | profile_id ↔ user_id linkage is what routes sync records to the correct cloud account
T65 | 16. Sync Engine | POST /v1/sync/push — receive records, LWW upsert, return queue_entry_id results | 4 | 6 Aug | 11 Aug | Push sync is the core of Phase 3; LWW conflict logic must be correct
T66 | 16. Sync Engine | SyncEngine.ts activation — read sync_queue, batch push, exponential backoff | 4 | 6 Aug | 11 Aug | SyncEngine activation is the mobile side of push; exponential backoff prevents hammering
T67 | 16. Sync Engine | GET /v1/sync/pull — records since cursor, server_updated_at in response | 3 | 12 Aug | 14 Aug | Pull sync enables multi-device; cursor must save atomically with applied results
T68 | 16. Sync Engine | Pull apply — LWW, local-pending-beats-pull rule, cursor persistence | 3 | 15 Aug | 19 Aug | Local-pending-beats-pull rule prevents pull from overwriting unsent local changes
T70 | 17. Shared Business Rules | Parity tests — seed identical state in SQLite + PostgreSQL, assert equal STS | 3 | 20 Aug | 22 Aug | Parity test is the Phase 3 correctness gate; any STS divergence is a blocking defect
T75 | 19. Premium QA | Full regression suite — all MVP tests still green post-Phase 3 | 2 | 25 Aug | 26 Aug | Zero regressions allowed; MVP tests must stay green after Phase 3 additions
ID | Group | Task | Days | Risk Reason
HIGH RISK TASKS — 16 tasks ¦ These warrant extra review time and regression testing.
T09 | 2. Database Layer | BillRepository + BillInstanceRepository — create, update, idempotent generation | 3 | Bill instance idempotency — duplicate instances silently double-deduct safe-to-spend
T16 | 3. Financial Engine | cycleBoundaries.ts — weekly/biweekly/semimonthly/monthly, month-end edge cases | 3 | Semimonthly cycle boundaries in February; month-end edge cases are where cycle bugs hide
T18 | 3. Financial Engine | safeToSpend.ts — pure function, all 6 inputs, negative result valid | 2 | Primary calculation — any bug instantly erodes user trust; must have 100% test coverage
T19 | 3. Financial Engine | billInstances.ts — fixed+variable generation, idempotency, paused exclusion | 3 | Duplicate bill generation is silent; users see doubled deductions, trust is gone
T27 | 4. Services Layer | ImportService — CSV parser, field stripping, file deletion, suggestion writing | 3 | Privacy-critical: one leaked account number is a serious user trust failure
T49 | 12. QA & Polish | Physical device QA — 7 acceptance scenarios on iOS + Android | 3 | Physical device behaviour differs from simulators; offline edge cases appear only on device
T52 | 12. QA & Polish | Import privacy verification — no sensitive fields, file deletion confirmed | 1 | Import parser sensitive field stripping — regex patterns must cover all bank statement formats
T56 | 13. Beta & Launch | Beta feedback triage + critical fixes + final store submission | 3 | App Store review is unpredictable; privacy label mistakes cause rejection
T65 | 16. Sync Engine | POST /v1/sync/push — receive records, LWW upsert, return queue_entry_id results | 4 | LWW conflict resolution — incorrect timestamp comparison corrupts PostgreSQL records
T66 | 16. Sync Engine | SyncEngine.ts activation — read sync_queue, batch push, exponential backoff | 4 | Sync retry backoff — too aggressive causes API hammering; too slow frustrates users
T67 | 16. Sync Engine | GET /v1/sync/pull — records since cursor, server_updated_at in response | 3 | Pull cursor persistence — cursor not saved = re-applying all changes = potential overwrites
T68 | 16. Sync Engine | Pull apply — LWW, local-pending-beats-pull rule, cursor persistence | 3 | Local-pending-beats-pull — implementing incorrectly causes local changes to be silently lost
T69 | 17. Shared Business Rules | Backend financial engine — mirror safeToSpend rules in Spring Boot | 4 | Backend engine parity — any rule divergence is a blocking defect; hardest to debug
T70 | 17. Shared Business Rules | Parity tests — seed identical state in SQLite + PostgreSQL, assert equal STS | 3 | Parity test setup is complex; requires seeding identical state across two database engines
T76 | 19. Premium QA | Multi-device conflict test — two devices edit same record, newer wins | 2 | Multi-device conflict simulation is hard to reproduce deterministically in tests
T80 | 20. Web Prep (Future) | Web client scaffolding — React web app, consume backend engine API | 5 | React web app is a large scope addition; deferred until premium sync is proven stable

## Milestones
Budget Flow — Milestone Breakdown
# | Milestone | Gate Task | Date | Duration | Definition of Done | Phase
M0 | Dev environment ready | T04 | 5 Jun 2025 | Week 1 | All developers can build, run, and test on both platforms. CI pipeline green. | MVP
M1 | Database layer complete | T13 | 18 Jun 2025 | Week 3 | Full schema applied, migration runner verified iOS+Android, FK enforcement confirmed, all repositories written and tested. | MVP
M2 | Financial engine proven correct | T22 | 20 Jun 2025 | Week 3 | 100% unit test coverage on all engine modules. All 7 acceptance scenarios pass. Test contracts documented in /docs/calculation-contracts/. | MVP
M3 | Navigation shell ready | T33 | 11 Jun 2025 | Week 2 | Bottom tab navigator working. ProfileContext and FinancialStateContext wired. Empty screens in place. | MVP
M4 | Dashboard working end-to-end | T35 | 30 Jun 2025 | Week 5 | Dashboard displays correct safe-to-spend from real SQLite data. EventBus recalculation triggered by purchase entry. | MVP
M5 | MVP feature complete | T47 | 2 Jul 2025 | Week 5 | All screens implemented. Backup/restore working. Onboarding complete. All financial actions recalculate safe-to-spend correctly. | MVP
M6 | App Store submitted | T56 | 22 Jul 2025 | Week 8 | App submitted to App Store and Google Play. Beta distribution active on TestFlight and Play Internal Testing track. | Polish
M7 | Sync scaffolding verified | T59 | 10 Jul 2025 | Week 6 | sync_queue audit complete — all repos write rows. Calculation contracts documented. SyncEngine stub in place, feature-flagged off. | MVP
M8 | Auth working | T64 | 5 Aug 2025 | Week 10 | JWT RS256 authentication working end-to-end. Token stored in Keychain. 401 refresh flow working. Tampered tokens rejected. | Premium
M9 | Sync + parity proven | T70 | 22 Aug 2025 | Week 12 | Bidirectional sync working. All 7 parity tests pass — mobile engine and backend engine produce identical safe-to-spend to the cent. | Premium
M10 | Premium launch | T78 | 1 Sep 2025 | Week 14 | Premium features live on App Store and Google Play. Backend deployed with monitoring. Feature flag flipped. | Premium
M11 | Web client foundation | T80 | 27 Aug 2025 | Week 13 | Web application scaffolding in place. Backend engine API serving safe-to-spend for web clients. | Future

## Mermaid Code
Budget Flow — Mermaid Gantt Code ¦ Paste into mermaid.live or any Markdown file
Copy all rows below this line into a ```mermaid code block in any .md file, Notion, GitHub, or mermaid.live
gantt
title Budget Flow — Professional Development Gantt
dateFormat YYYY-MM-DD
axisFormat %d %b
section MVP Phase
%% -- 1. Planning & Setup --
Project init — RN+TS ESLint Prettier Jest folder struct :T01, 2025-06-02, 3d
SQLite library selection + native module verification ( :crit, T02, 2025-06-05, 2d
CI pipeline — GitHub Actions test runner branch protect :T03, 2025-06-05, 2d
Development environment docs + .env templates (dev/stag [M: M0: Dev environment ready] :T04, 2025-06-05, 1d
%% -- 2. Database Layer --
Full SQLite schema — all tables indexes UNIQUE constrai :crit, T05, 2025-06-09, 4d
Migration runner — versioned SQL files schema_version t :crit, T06, 2025-06-09, 2d
ProfileRepository — single row essential_reserve onboar :crit, T07, 2025-06-13, 2d
PaycheckRepository — create confirm findCurrentCycle so :crit, T08, 2025-06-17, 2d
BillRepository + BillInstanceRepository — create update :crit, T09, 2025-06-17, 3d
PurchaseRepository — create softDelete findAll (deleted :crit, T10, 2025-06-17, 2d
BalanceAdjustmentRepository + ActivityLogRepository (ap :T11, 2025-06-17, 2d
SyncQueueRepository — write path only (read path deferr :T12, 2025-06-17, 2d
NotificationSettingsRepository + ImportSuggestionReposi [M: M1: Database layer complete] :T13, 2025-06-17, 2d
%% -- 3. Financial Engine --
currency.ts — integer cent arithmetic formatCurrency() :crit, T14, 2025-06-05, 1d
dates.ts — ISO 8601 parsing UTC helpers cycle membershi :crit, T15, 2025-06-05, 1d
cycleBoundaries.ts — weekly/biweekly/semimonthly/monthl :crit, T16, 2025-06-06, 3d
balance.ts — running balance from confirmed paychecks p :crit, T17, 2025-06-06, 2d
safeToSpend.ts — pure function all 6 inputs negative re :crit, T18, 2025-06-10, 2d
billInstances.ts — fixed+variable generation idempotenc :crit, T19, 2025-06-11, 3d
variableBills.ts — estimate from last confirmed confirm :T20, 2025-06-16, 2d
projections.ts — forward cycle projections for paycheck :T21, 2025-06-16, 2d
7 acceptance test scenarios (A–G) + test contract docum [M: M2: Financial engine proven correct] :crit, T22, 2025-06-18, 3d
%% -- 4. Services Layer --
DashboardService — query repos call engine return Dashb :crit, T23, 2025-06-19, 2d
PurchaseService — createPurchase deletePurchase recalc :crit, T24, 2025-06-23, 2d
PaycheckService — create confirm generateBillInstances :crit, T25, 2025-06-23, 2d
BillService — create update generateInstancesForCycle c :crit, T26, 2025-06-20, 3d
ImportService — CSV parser field stripping file deletio :T27, 2025-06-19, 3d
BackupService — JSON export restore with validation + a :T28, 2025-06-17, 3d
ActivityLogService + NotificationService (local pending :T29, 2025-06-17, 2d
%% -- 5. Navigation & UI Shell --
Bottom tab navigator + screen containers + navigation l :T30, 2025-06-06, 2d
ProfileContext — load profile on startup gate navigatio :crit, T31, 2025-06-17, 1d
FinancialStateContext + EventBus — FINANCIAL_STATE_CHAN :crit, T32, 2025-06-23, 2d
Shared UI components — currency display date formatting [M: M3: Navigation shell ready] :T33, 2025-06-10, 2d
%% -- 6. Dashboard --
DashboardScreen — safe-to-spend hero upcoming bills nex :crit, T34, 2025-06-25, 3d
Safe-to-spend negative state display — red styling no c [M: M4: Dashboard working end-to-end] :T35, 2025-06-30, 1d
%% -- 7. Purchases --
PurchasesScreen — transaction list cycle grouping pendi :crit, T36, 2025-06-25, 2d
PurchaseEntrySheet — amount input charged/pending toggl :crit, T37, 2025-06-27, 2d
%% -- 8. Bills --
BillsScreen — cycle grouping due-date sort fixed vs var :crit, T38, 2025-06-25, 2d
VariableBillConfirmSheet — enter actual amount trigger :T39, 2025-06-27, 2d
Bill add/edit form — recurrence interval end date pause :T40, 2025-06-27, 2d
%% -- 9. Paychecks --
PaychecksScreen — cycle cards projected vs confirmed st :T41, 2025-06-25, 3d
Paycheck confirm flow — mark received trigger bill inst :crit, T42, 2025-06-30, 1d
%% -- 10. Import --
ImportScreen — file picker processing state privacy con :T43, 2025-06-24, 2d
SuggestionReviewScreen — confirm/reject each detected r :T44, 2025-06-26, 2d
%% -- 11. Settings & Backup --
SettingsScreen — reserve config notification prefs back :T45, 2025-06-25, 2d
BackupRestoreScreen — export import file validation fee :T46, 2025-06-27, 2d
Onboarding flow — skippable steps partial dashboard sti [M: M5: MVP feature complete] :T47, 2025-06-30, 3d
%% -- 12. QA & Polish --
Integration test suite — sync_queue writes soft deletes :crit, T48, 2025-07-03, 3d
Physical device QA — 7 acceptance scenarios on iOS + An :crit, T49, 2025-07-08, 3d
Performance audit — STS recalc < 50ms SQLite EXPLAIN QU :T50, 2025-07-11, 2d
Accessibility pass — VoiceOver (iOS) + TalkBack (Androi :T51, 2025-07-11, 2d
Import privacy verification — no sensitive fields file :crit, T52, 2025-07-11, 1d
%% -- 13. Beta & Launch --
Crash reporting setup — Sentry beforeSend strips all fi :T53, 2025-07-11, 2d
App Store + Play Store assets — screenshots description :T54, 2025-07-11, 3d
TestFlight (iOS) + Internal Testing (Android) beta dist :T55, 2025-07-16, 2d
Beta feedback triage + critical fixes + final store sub [M: M6: App Store submitted — MVP shipped] :T56, 2025-07-18, 3d
%% -- 14. Sync Prep --
sync_queue audit — verify all repos write rows on creat :T57, 2025-07-08, 2d
Calculation contracts documentation — /docs/calculation :T58, 2025-06-23, 2d
SyncEngine stub — feature-flagged no-op FEATURE_PREMIUM [M: M7: MVP sync scaffolding verified] :T59, 2025-07-10, 1d
section Premium Sync (Phase 3)
%% -- 15. Backend Setup --
Spring Boot project init — modules PostgreSQL schema (+ :T60, 2025-07-23, 4d
Auth module — register bcrypt login JWT RS256 sign/veri :crit, T61, 2025-07-29, 4d
Accounts module — profile_id ↔ user_id linkage first-sy :crit, T62, 2025-08-04, 2d
Mobile auth UI — registration/login screens Keychain/Ke :T63, 2025-07-29, 3d
401 interceptor + token refresh logic in API client [M: M8: Auth working] :T64, 2025-08-04, 2d
%% -- 16. Sync Engine --
POST /v1/sync/push — receive records LWW upsert return :crit, T65, 2025-08-06, 4d
SyncEngine.ts activation — read sync_queue batch push e :crit, T66, 2025-08-06, 4d
GET /v1/sync/pull — records since cursor server_updated :crit, T67, 2025-08-12, 3d
Pull apply — LWW local-pending-beats-pull rule cursor p :crit, T68, 2025-08-15, 3d
%% -- 17. Shared Business Rules --
Backend financial engine — mirror safeToSpend rules in :T69, 2025-08-12, 4d
Parity tests — seed identical state in SQLite + Postgre [M: M9: Sync + parity proven] :crit, T70, 2025-08-20, 3d
%% -- 18. Cloud & Notifications --
Cloud backup endpoints — POST/GET /v1/backup :T71, 2025-08-06, 2d
Cloud backup UI — enable toggle restore from cloud in S :T72, 2025-08-08, 2d
Server-side notifications — APNs + FCM calm tone bill r :T73, 2025-08-12, 3d
Premium UX — sync status premium onboarding notificatio :T74, 2025-08-15, 3d
%% -- 19. Premium QA --
Full regression suite — all MVP tests still green post- :crit, T75, 2025-08-25, 2d
Multi-device conflict test — two devices edit same reco :T76, 2025-08-25, 2d
Backend deploy — PostgreSQL Spring Boot health checks m :T77, 2025-08-27, 2d
Premium store update + feature flag flip + launch [M: M10: Premium launch] :T78, 2025-08-29, 2d
section Future — Web Support
%% -- 20. Web Prep (Future) --
Backend engine web API endpoints — serve STS for web cl :T79, 2025-08-18, 3d
Web client scaffolding — React web app consume backend [M: M11: Web client foundation] :T80, 2025-08-21, 5d